## Sheet1
| name | due
0 | Engineer - View List of Ideas - 40 - to be split | 2020-03-13T20:53:00.000Z
1 | Web Designer - Download files in View list of ideas | 2020-03-13T20:53:00.000Z
2 | Web Designer - Adjust styling to comply to brand and accessibility guidelines as well as the prototype
3 | Web Designer - view of most popular ideas | 2020-03-06T20:53:00.000Z
4 | Engineer - Manage Forums
5 | Engineer - Display Comments Design and Logic integration
6 | Web Designer - Idea Submission - Document Upload | 2020-03-13T20:53:00.000Z
7 | Web Designer - Administration Panel For QA manager - Data export to CSV after final closure date, attachment export to zip - 8 | 2020-03-13T20:53:00.000Z
8 | Engineer - Administration Panel For QA manager - Data export to CSV after final closure date, attachment export to zip - 8 | 2020-03-13T20:53:00.000Z
9 | Engineer - Terms and conditions | 2020-03-13T20:53:00.000Z
10 | Web Designer - Terms and conditions | 2020-03-13T20:53:00.000Z
11 | Tester - component integration testing | 2020-03-13T20:53:00.000Z
12 | Engineer - component integration fixes | 2020-03-13T20:53:00.000Z
13 | Everyone - Documentation | 2020-03-13T20:53:00.000Z
14 | Web Designer / Engineer - UX bug fixes | 2020-03-13T20:53:00.000Z
15 | Product Owner - Create a screen recording of ready product | 2020-03-13T20:53:00.000Z
16 | Scrum Master - Submit the group report | 2020-03-24T20:53:00.000Z
17 | Refactoring code
18 | Engineer - View Ideas | 2020-02-21T20:53:00.000Z
19 | Engineer - Merge reports.php and analytics.php
20 | Engineer - Add link to terms and conditions to a blank page that throws notImplementedException
21 | Everyone - record the presentation of a product | 2020-03-23T20:53:00.000Z
22 | Scrum Master - Update Information Architecture Visualisation by including loginreg step prior to any other step | 2020-03-20T01:57:00.000Z
23 | Tester - Test idea submission | 2020-02-14T20:53:00.000Z
24 | Scrum Master - Start Filling in The testing bits of finished pages | 2020-03-20T01:57:00.000Z
25 | Scrum Master - Grooming - Ensure that everything works
26 | Engineer - Add report offensive comment to view_ideas.php
27 | Engineer - Link qa management page links with QAM.php and analytics.php
28 | Engineer - Fix Inform user of successful registration
29 | Engineer - Administration Panel For QA manager - add additional categories at any time, and can delete categories, | 2020-03-13T20:53:00.000Z
30 | Engineer - Reporting of Inappropriate posts - Add report offensive comment to view_ideas.php
31 | Engineer - QA Manager to disable an account and remove all his ideas and comments
32 | Engineer - QA Manager to unblock user, to restore all ideas and comments of user
33 | Web Designer - Accessibility Testing
34 | Engineer - View ideas.php take into consideration blocked users
35 | Web Designer / Engineer - Merge submit_ideas.php and view_ideas.php | 2020-03-20T20:53:00.000Z
36 | Engineer - View_ideas.php hide submit comment, voting and download features if logged out
37 | Tester - UX Test | 2020-03-06T20:53:00.000Z
38 | QA-management: Edit Categories and closure dates + download data UX
39 | Engineer - Email Notification of new idea to department QA coordinator. Notification to author about comments. - 5 | 2020-03-13T20:53:00.000Z
40 | Engineer - fix view_ideas.php displaying 4 ideas, add pagination | 2020-03-20T20:42:00.000Z
41 | Engineer - page view analytics | 2020-03-20T21:22:00.000Z
42 | Engineer - Last Login date | 2020-03-20T21:22:00.000Z
43 | Engineer - QA Manager to block users from posting ideas and comments | 2020-03-13T20:53:00.000Z
44 | Engineer - Fix registration | 2020-03-20T21:22:00.000Z
45 | Web Designer - Branding Pack | 2020-02-28T20:53:00.000Z
46 | Web Designer - Administrator panel to maintain system data -13 | 2020-03-13T20:53:00.000Z
47 | Engineer - Idea Submission - Document Upload | 2020-03-13T20:53:00.000Z
48 | Engineer - Encryption | 2020-03-13T01:57:00.000Z
49 | Tester - Compliance Testing | 2020-03-06T20:53:00.000Z
50 | Scrum Master - to fix view_ideas.pho | 2020-03-13T01:57:00.000Z
51 | Engineer - View Idea | 2020-03-13T20:53:00.000Z
52 | Engineer - Forum selection | 2020-02-28T20:53:00.000Z
53 | Engineer - Download files in View list of ideas | 2020-02-21T20:53:00.000Z
54 | Scrum Master - Information Architecture | 2020-03-13T01:57:00.000Z
55 | Engineer - Migrate Database from Uni DB to Hosting DB | 2020-03-13T20:53:00.000Z
56 | Web Designer - Administration Panel For QA manager | 2020-03-13T20:53:00.000Z
57 | Database - Alter Tables to reflect requirement change | 2020-03-06T20:53:00.000Z
58 | Tester - Test login and registration | 2020-02-14T20:53:00.000Z
59 | Web Designer / Engineer - Merge loginreg.html and loginreg.php | 2020-02-28T20:53:00.000Z
60 | Engineer - Administrator panel to maintain system data -13 | 2020-02-21T20:53:00.000Z
61 | Web Designer - Manage Users | 2020-03-06T14:11:00.000Z
62 | Tester - Create System Test Cases | 2020-02-21T20:53:00.000Z
63 | Scrum Master - Add database creation and population scripts to repo and Appendix in the report | 2020-02-28T20:53:00.000Z
64 | Engineer - Navigation | 2020-02-28T20:53:00.000Z
65 | Engineer - Idea Submission | 2020-02-14T20:40:00.000Z
66 | Web Designer - Thumbs up / down for ideas - 4 | 2020-02-28T20:53:00.000Z
67 | Engineer - Thumbs up / down for ideas - 4 | 2020-02-28T20:53:00.000Z
68 | Engineer - Add comments for Idea | 2020-02-28T20:53:00.000Z
69 | Web Designer - Add comments for Idea | 2020-02-28T20:53:00.000Z
70 | Moved analytics.html to analytics.php(View statistics for the different ideas and departments, etc) | 2020-02-21T20:53:00.000Z
71 | Moved ideasubmission.html to submit_idea.php (this page shows the list of ideas and allows the user to add an idea) | 2020-02-21T20:53:00.000Z
72 | Forum.html has been moved to forum.php (On this page, you can view the list of forums and select which one to go in) | 2020-02-21T20:53:00.000Z
73 | discussion.html has been moved to view_idea.php (On this page, the user is able to see the comments on a selected idea or more details...) | 2020-02-21T20:53:00.000Z
74 | Web Designer - Single Idea View | 2020-02-21T20:53:00.000Z
75 | Moved admin.html to admin_panel.php | 2020-02-21T20:53:00.000Z
76 | Engineer - Logout component - 1 | 2020-02-21T20:53:00.000Z
77 | Engineer - Logout Component Integration
78 | Scrum Master - Our Definition of Done (Add in Description) | 2020-02-21T19:58:00.000Z
79 | Web Designer - Display Comments | 2020-02-21T20:53:00.000Z
80 | Engineer - Display Comments | 2020-02-21T22:09:00.000Z
81 | Engineer - Integrate Login and registration with Database | 2020-02-14T14:05:00.000Z
82 | Web Designer - Statistical analysis - 5 | 2020-02-21T20:53:00.000Z
83 | Web Designer - View List of Ideas | 2020-02-21T20:53:00.000Z
84 | Web Designer - Idea Submission | 2020-02-21T20:53:00.000Z
85 | Tester - Integration Testing | 2020-02-21T20:53:00.000Z
86 | Web Designer - View List of Ideas | 2020-02-21T20:53:00.000Z
87 | Tester - Compliance Testing | 2020-02-21T20:53:00.000Z
88 | Tester - Implement test plan for list of ideas and forum selection | 2020-02-14T20:53:00.000Z
89 | Engineer - Statistical analysis - 5 | 2020-02-21T20:53:00.000Z
90 | Engineer - View of most popular ideas | 2020-02-21T20:53:00.000Z
91 | Engineer - View List of Ideas - Simple grid view | 2020-02-14T20:53:00.000Z
92 | Scrum Master - Consolidate all the existing material into one report | 2020-02-14T20:53:00.000Z
93 | Web Designer - Implement Design For Views - Registration and login | 2020-02-07T19:45:00.000Z
94 | Web Designer - Implement Design for Mobile views - Registration and Login | 2020-02-07T19:45:00.000Z
95 | Database Designer - Testing database SQL commands | 2020-02-14T20:11:00.000Z
96 | Database Designer - Database CRUD class validation | 2020-02-14T20:11:00.000Z
97 | Database Designer - Research PDO database connections - 2 hours | 2020-02-14T20:11:00.000Z
98 | Scrum Master - Burndown Chart | 2020-02-07T20:40:00.000Z
99 | Product Owner - analyse project's example report, create report skeleton | 2020-02-07T20:40:00.000Z
100 | Web Designer - Implement mobile website design sketch | 2020-02-07T20:40:00.000Z
101 | Database Designer - Database CRUD class - 20 hours | 2020-02-14T19:45:00.000Z
102 | Web Designer - Implement website design sketch | 2020-02-03T20:40:00.000Z
103 | Engineer - Create database population script | 2020-02-07T14:05:00.000Z
104 | Build database - Sam and James - 1 hour | 2020-02-07T20:58:00.000Z
105 | Engineer - Log In and Registration | 2020-02-07T19:45:00.000Z
106 | Web Designer - Log In and Registration - 5 | 2020-02-07T20:40:00.000Z
107 | Tester - Implement Test Plan for login, registration and idea submission | 2020-02-07T20:53:00.000Z
108 | Database Designer - Legal and Ethical research for Database Design | 2020-02-07T20:40:00.000Z
109 | Scrum Master - Breakdown work into more detailed stories | 2020-02-07T19:45:00.000Z
110 | Database Designer - Database Design - 13 - Sam James - 5 | 2020-01-31T19:45:00.000Z
111 | Scrum Master - System Architecture Design - 5 - 0.5 | 2020-01-31T19:45:00.000Z
112 | Scrum Master - assign roles - 1 - 0.1 | 2020-01-31T19:45:00.000Z
113 | Scrum Master - Establish agile scrum methods - 5 - 2 | 2020-01-31T19:45:00.000Z