## Sheet1
| name | due
0 | Engineer - View List of Ideas - 40 - to be split | 2020-03-13T20:53:00.000Z
1 | Engineer - Last Login date
2 | Engineer - page view analytics
3 | Engineer - Reporting of Inappropriate posts
4 | Engineer - QA Manager to block users from posting ideas and comments
5 | Web Designer - Download files in View list of ideas | 2020-03-13T20:53:00.000Z
6 | Engineer - QA Manager to disable an account and remove all his ideas and comments
7 | Engineer - QA Manager to unblock user, to restore all ideas and comments of user
8 | Engineer - Merge reports.php and analytics.php
9 | Engineer - Display Comments Design and Logic integration
10 | Engineer - View Idea | 2020-03-13T20:53:00.000Z
11 | Web Designer - Idea Submission - Document Upload | 2020-03-13T20:53:00.000Z
12 | Engineer - Idea Submission - Document Upload | 2020-03-13T20:53:00.000Z
13 | Web Designer - view of most popular ideas | 2020-03-06T20:53:00.000Z
14 | Web Designer - Administration Panel For QA manager | 2020-03-13T20:53:00.000Z
15 | Engineer - Administration Panel For QA manager | 2020-03-13T20:53:00.000Z
16 | Web Designer - Administration Panel For QA manager - Data export to CSV after final closure date, attachment export to zip - 8 | 2020-03-13T20:53:00.000Z
17 | Engineer - Administration Panel For QA manager - Data export to CSV after final closure date, attachment export to zip - 8 | 2020-03-13T20:53:00.000Z
18 | Engineer - Terms and conditions | 2020-03-13T20:53:00.000Z
19 | Web Designer - Terms and conditions | 2020-03-13T20:53:00.000Z
20 | Web Designer - Administrator panel to maintain system data -13
21 | Engineer - Notification of new idea to department QA coordinator. Notification to author about comments. - 5 | 2020-03-13T20:53:00.000Z
22 | Tester - component integration testing | 2020-03-13T20:53:00.000Z
23 | Engineer - component integration fixes | 2020-03-13T20:53:00.000Z
24 | Engineer - Migrate Database from Uni DB to Hosting DB | 2020-03-13T20:53:00.000Z
25 | Everyone - Documentation | 2020-03-13T20:53:00.000Z
26 | Web Designer / Engineer - UX bug fixes | 2020-03-13T20:53:00.000Z
27 | Product Owner - Create a screen recording of ready product | 2020-03-13T20:53:00.000Z
28 | Everyone - Present the product | 2020-03-13T20:53:00.000Z
29 | Scrum Master - Submit the group report | 2020-03-24T20:53:00.000Z
30 | Refactoring code
31 | Engineer - View Ideas | 2020-02-21T20:53:00.000Z
32 | Tester - UX Test | 2020-03-06T20:53:00.000Z
33 | Web Designer / Engineer - Merge submit_ideas.php and view_ideas.php | 2020-02-28T20:53:00.000Z
34 | Tester - Test idea submission | 2020-02-14T20:53:00.000Z
35 | Web Designer - Accessibility Testing
36 | Tester - Compliance Testing | 2020-03-06T20:53:00.000Z
37 | Web Designer - Branding Pack | 2020-02-28T20:53:00.000Z
38 | Engineer - Forum selection | 2020-02-28T20:53:00.000Z
39 | Engineer - Download files in View list of ideas | 2020-02-21T20:53:00.000Z
40 | Engineer - Idea Submission | 2020-02-14T20:40:00.000Z
41 | Database - Alter Tables to reflect requirement change | 2020-03-06T20:53:00.000Z
42 | Tester - Test login and registration | 2020-02-14T20:53:00.000Z
43 | Web Designer / Engineer - Merge loginreg.html and loginreg.php | 2020-02-28T20:53:00.000Z
44 | Engineer - Administrator panel to maintain system data -13 | 2020-02-21T20:53:00.000Z
45 | Web Designer - Manage Users | 2020-03-06T14:11:00.000Z
46 | Tester - Create System Test Cases | 2020-02-21T20:53:00.000Z
47 | Scrum Master - Add database creation and population scripts to repo and Appendix in the report | 2020-02-28T20:53:00.000Z
48 | Engineer - Navigation | 2020-02-28T20:53:00.000Z
49 | Web Designer - Thumbs up / down for ideas - 4 | 2020-02-28T20:53:00.000Z
50 | Engineer - Thumbs up / down for ideas - 4 | 2020-02-28T20:53:00.000Z
51 | Engineer - Add comments for Idea | 2020-02-28T20:53:00.000Z
52 | Web Designer - Add comments for Idea | 2020-02-28T20:53:00.000Z
53 | Moved analytics.html to analytics.php(View statistics for the different ideas and departments, etc) | 2020-02-21T20:53:00.000Z
54 | Moved ideasubmission.html to submit_idea.php (this page shows the list of ideas and allows the user to add an idea) | 2020-02-21T20:53:00.000Z
55 | Forum.html has been moved to forum.php (On this page, you can view the list of forums and select which one to go in) | 2020-02-21T20:53:00.000Z
56 | discussion.html has been moved to view_idea.php (On this page, the user is able to see the comments on a selected idea or more details...) | 2020-02-21T20:53:00.000Z
57 | Web Designer - Single Idea View | 2020-02-21T20:53:00.000Z
58 | Moved admin.html to admin_panel.php | 2020-02-21T20:53:00.000Z
59 | Engineer - Logout component - 1 | 2020-02-21T20:53:00.000Z
60 | Engineer - Logout Component Integration
61 | Scrum Master - Our Definition of Done (Add in Description) | 2020-02-21T19:58:00.000Z
62 | Web Designer - Display Comments | 2020-02-21T20:53:00.000Z
63 | Engineer - Display Comments | 2020-02-21T22:09:00.000Z
64 | Engineer - Integrate Login and registration with Database | 2020-02-14T14:05:00.000Z
65 | Web Designer - Statistical analysis - 5 | 2020-02-21T20:53:00.000Z
66 | Web Designer - View List of Ideas | 2020-02-21T20:53:00.000Z
67 | Web Designer - Idea Submission | 2020-02-21T20:53:00.000Z
68 | Tester - Integration Testing | 2020-02-21T20:53:00.000Z
69 | Web Designer - View List of Ideas | 2020-02-21T20:53:00.000Z
70 | Tester - Compliance Testing | 2020-02-21T20:53:00.000Z
71 | Tester - Implement test plan for list of ideas and forum selection | 2020-02-14T20:53:00.000Z
72 | Engineer - Statistical analysis - 5 | 2020-02-21T20:53:00.000Z
73 | Engineer - View of most popular ideas | 2020-02-21T20:53:00.000Z
74 | Engineer - View List of Ideas - Simple grid view | 2020-02-14T20:53:00.000Z
75 | Scrum Master - Consolidate all the existing material into one report | 2020-02-14T20:53:00.000Z
76 | Web Designer - Implement Design For Views - Registration and login | 2020-02-07T19:45:00.000Z
77 | Web Designer - Implement Design for Mobile views - Registration and Login | 2020-02-07T19:45:00.000Z
78 | Database Designer - Testing database SQL commands | 2020-02-14T20:11:00.000Z
79 | Database Designer - Database CRUD class validation | 2020-02-14T20:11:00.000Z
80 | Database Designer - Research PDO database connections - 2 hours | 2020-02-14T20:11:00.000Z
81 | Scrum Master - Burndown Chart | 2020-02-07T20:40:00.000Z
82 | Product Owner - analyse project's example report, create report skeleton | 2020-02-07T20:40:00.000Z
83 | Web Designer - Implement mobile website design sketch | 2020-02-07T20:40:00.000Z
84 | Database Designer - Database CRUD class - 20 hours | 2020-02-14T19:45:00.000Z
85 | Web Designer - Implement website design sketch | 2020-02-03T20:40:00.000Z
86 | Engineer - Create database population script | 2020-02-07T14:05:00.000Z
87 | Build database - Sam and James - 1 hour | 2020-02-07T20:58:00.000Z
88 | Engineer - Log In and Registration | 2020-02-07T19:45:00.000Z
89 | Web Designer - Log In and Registration - 5 | 2020-02-07T20:40:00.000Z
90 | Tester - Implement Test Plan for login, registration and idea submission | 2020-02-07T20:53:00.000Z
91 | Database Designer - Legal and Ethical research for Database Design | 2020-02-07T20:40:00.000Z
92 | Scrum Master - Breakdown work into more detailed stories | 2020-02-07T19:45:00.000Z
93 | Database Designer - Database Design - 13 - Sam James - 5 | 2020-01-31T19:45:00.000Z
94 | Scrum Master - System Architecture Design - 5 - 0.5 | 2020-01-31T19:45:00.000Z
95 | Scrum Master - assign roles - 1 - 0.1 | 2020-01-31T19:45:00.000Z
96 | Scrum Master - Establish agile scrum methods - 5 - 2 | 2020-01-31T19:45:00.000Z